## Slide 1
VEGO-AI · SUPERVISOR DECISION CHECKPOINT
Approve the doctoral spine
and protect the evidence boundary
Iris Reinhartz-Berger · Arnon Sturm · Ali Hamed
5 August 2026 · weekly supervisor meeting
Notes: 0:00–0:30 — State the purpose: approve or precisely correct the architecture and close with one task.
State that this is the weekly supervisor package, not the candidacy or Penina presentation.
[Sources]
- docs/research/meetings/2026-08-05-supervisor-presentation-checklist.md
- docs/research/meetings/2026-08-05-supervisor-pre-read.md

## Slide 2
All known controls are captured; acceptance remains open
2
The package is traceable and evidence-linked, but human and external gates still control completion.
44/44
controls captured
19 requirements · 15 actions · 10 questions
2
narrowly verified
A-03 workbook seed and A-06 calendar recurrence
0/19
requirements accepted
Iris/Arnon decisions are not yet recorded
Notes: 0:30–1:10 — Emphasize the difference between capture, implementation, and acceptance.
Do not say 44/44 complete. State the current distribution: 6 awaiting, 22 partial, 5 open, 9 blocked.
[Sources]
- docs/research/phd-proposal/iris-requirements-closure-audit.md
- docs/research/phd-proposal/master-traceability-register.md

## Slide 3
One doctoral spine connects intervention, governance, and transfer
3
Umbrella research question
How can reusable human judgment be captured, governed, and reused in agentic AI assessment?
Goal: auditable, reliable, and transferable human–AI co-reasoning.
Exactly three subquestions
SQ1 · When should the system request human judgment?
SQ2 · How should judgment be governed and safely reused?
SQ3 · What quality, traceability, effort, and transfer effects result?
Notes: 1:10–2:10 — Read the four conceptual slots; alternatives are wording variants, not additional RQs.
Request D-RQ-01 and D-RQ-02. Record exact corrections.
[Sources]
- docs/research/phd-proposal/2026-08-05-rq-decision-pack.md
- docs/research/meetings/2026-07-29-iris-requirements-register.md (R-01, R-07, R-08)

## Slide 4
Each subquestion has one study, artifact, and fallback
4
Study 1 · Intervention
Design science + trigger, timing, dosage, routing, burden, timeout and conformance tests.
Study 2 · Judgment lifecycle
Provenance, validation, conflict, authority, expiry, retrieval and unsafe-reuse tests.
Study 3 · Evaluation
Blinded reviewers, adjudication, paired outcomes, effort/usability and transfer limits.
Common fallback
All three questions remain answerable under Plan B; medicine is not the only completion path.
Notes: 2:10–3:05 — Connect each SQ to method, evidence, artifact, metrics, risk and fallback.
Request D-RQ-03. Outcomes remain planned until protocols and human evidence run.
[Sources]
- docs/research/phd-proposal/three-study-contract.md
- docs/research/phd-proposal/2026-08-05-rq-decision-pack.md#4-study-mapping

## Slide 5
Legacy questions are absorbed—not silently deleted
5
What is preserved
Every earlier five- or six-question set keeps a recorded disposition.
Useful constructs remain as study variables, evaluation measures, or supporting questions.
What changes
One umbrella RQ and three SQs become the proposal spine.
Duplicate, evaluation-only, or out-of-scope wording is retired transparently.
Notes: 3:05–3:35 — This slide prevents scope fragmentation and shows that prior work is not discarded.
Ask only whether the crosswalk logic is acceptable; do not reopen every legacy wording item.
[Sources]
- docs/research/phd-proposal/legacy-rq-crosswalk.md
- docs/research/phd-proposal/legacy-decision-disposition.md

## Slide 6
Plan B protects doctoral completion; Plan A is conditional
6
Plan B · committed fallback
Complete Studies 1–3 in software/modeling plus an authorized non-medical replication.
Same RQs, doctoral scale, evaluation, and publication outputs.
Executable without clinician, medical data, VDI, or ethics dependencies.
Plan A · staged extension
Add a bounded medical transfer only after G1–G6 pass.
If any critical gate is not evidenced by 26 August, Plan B becomes the September baseline.
The date and rule remain proposed until D-RQ-04–06 are decided.
Notes: 3:35–4:30 — Ask D-RQ-04, D-RQ-05 and, if time permits, D-RQ-06.
Make clear that the 26 August date is an internal proposed control, not a July 29 approval.
[Sources]
- docs/research/phd-proposal/2026-08-05-rq-decision-pack.md#5-plan-a-and-plan-b-for-confirmation
- docs/research/governance/medical-readiness-scorecard.md

## Slide 7
Literature system ready; review remains open
7
One paper per row; authors’ evidence remains separate from Ali’s synthesis.
Workstream | Artifact now | Evidence state | Next proof
Search protocol | Databases, concepts, dates, screening fields | Prepared | Execute and date queries
Workbook | Six tabs + controlled fields + six seeds | Verified narrow build | Verify every seed and DOI
Screening | Inclusion/exclusion fields | NOT RUN | Deduplicate and screen
Synthesis | Taxonomy and gap views | NOT RUN | Compare claims, limits and contradictions
Novelty | Candidate linked lifecycle contribution | Preliminary | Supervisor-reviewed corpus evidence
Notes: 4:30–5:15 — Request D-RQ-08 only if time permits.
Do not call the literature review or novelty case complete; the structure and seed tranche are the only narrow completions.
[Sources]
- docs/research/phd-proposal/literature-review-protocol.md
- docs/research/phd-proposal/master-traceability-register.md (R-15, R-16, A-02, A-03)

## Slide 8
Current evidence supports mechanisms—not outcome claims
8
0/24
EXP-005 safe labels
0/6
medical readiness gates
25/26
observed MIMIC tables; provenance unresolved
Chart: 
| Verified | Awaiting | Partial | Open | Blocked
Controls | 2 | 6 | 22 | 5 | 9
Notes: 6:15–7:10 — The bar chart is the audited control-state distribution, not scientific performance.
Say explicitly: mechanism/readiness evidence exists; accuracy, generalization, effort reduction, and clinical benefit do not.
[Sources]
- docs/research/phd-proposal/iris-requirements-closure-audit.md
- docs/research/phd-proposal/claim-register.md
- docs/research/governance/mimic-metadata-audit-2026-07-30.md
- reports/generated/exp005_label_review/ (current safe-label gate: 0/24)

## Slide 9
Medical work remains no-go until all six gates pass
9
The current MIMIC work is metadata/schema familiarization only; no patient rows were inspected.
Gate | Required proof | Current | Consequence
G1 Use case | Workflow, owner, unit, I/O, success | Open | No medical design
G2 People | Clinician, custodian, ethics, VDI admin | Open | No accountable route
G3 Authorization | Named-user project permission | Open | No row access
G4 Ethics/privacy | Written project determination | Open | No derived data
G5 Environment | Approved VDI, storage, logging, offline tools | Open | No processing
G6 Protocol | Cohort/outcome/mapping/leakage/statistics | Open | No experiment
Notes: 7:10–8:00 — State 0/6, 25/26 observed tables and missing NOTEEVENTS/provenance.
Ask D-RQ-09 and the medical-owner portion of D-RQ-10 if time permits.
No online/commercial model and no row-level work are authorized.
[Sources]
- docs/research/governance/medical-readiness-scorecard.md
- docs/research/governance/mimic-metadata-audit-2026-07-30.md
- docs/research/governance/phd-data-boundary.md

## Slide 10
The schedule advances while external rules remain open
10
5 AUG
Architecture decision
RQ/study/Plan A–B/claim decisions plus one next task.
26 AUG
Medical go/no-go
6/6 permits consideration; 0–5/6 activates Plan B.
SEP–OCT
Proposal convergence
Working targets only until Graduate Studies confirms policy and dates.
Notes: 8:00–8:45 — Calendar recurrence is confirmed; weekly execution quality is not yet evidenced.
Drive sharing, official candidacy rules, Penina dates and Iris availability require explicit confirmation.
[Sources]
- docs/research/phd-proposal/resource-raci-raid-register.md
- docs/research/phd-proposal/university-process-verification-checklist.md
- docs/research/phd-proposal/drive-workspace-manifest.md

## Slide 11
Resolve six decisions before discussing optional details
11
Allowed outcomes: Approve · Approve with correction · Defer · Reject. Silence is Defer.
Decision | Required outcome | Why now
D-RQ-01 | Umbrella-RQ wording | Locks the proposal spine
D-RQ-02 | Exactly three SQs | Prevents renewed fragmentation
D-RQ-03 | Three-study mapping | Locks method direction
D-RQ-04 | Plan A/B definitions | Protects feasibility
D-RQ-05 | Every RQ answerable in Plan B | Protects completion
D-RQ-07 | Five-state evidence boundary | Prevents overclaiming
Notes: 8:45–10:00 — Pause after each decision and capture exact wording, approver and rationale.
D-RQ-06, 08, 09 and owner assignment D-RQ-10 remain available in the appendix/pre-read.
[Sources]
- docs/research/phd-proposal/2026-08-05-rq-decision-pack.md#7-decisions-requested
- docs/research/meetings/2026-08-05-supervisor-presentation-checklist.md#decision-worksheet

## Slide 12
MEETING CLOSE
Read back every decision
Then select exactly one next task
Owner · due date and timezone · evidence path
Definition of done · dependency · fallback · claim boundary
12
Notes: 10:00–11:00 — Read back exact decisions and corrections.
Do not close until one primary task has owner, due date, evidence and definition of done.
A deferred item remains open and is not converted into acceptance.
[Sources]
- docs/templates/weekly-supervisor-pre-read.md
- docs/research/phd-proposal/decision-change-log.md

## Slide 13
Appendix · Requirements R-01–R-10
A1
Every baseline control is reachable from the deck; status remains evidence-bound.
ID
R-01
R-02
R-03
R-04
R-05
R-06
R-07
R-08
R-09
R-10
Control
One umbrella RQ + exactly three SQs
Each SQ maps to one study contract
Proposal contains all six required areas
Novelty, scale, feasibility, resources, schedule
Concise candidacy presentation
Research continues while administration proceeds
Every RQ answerable without medicine
Separate current software evidence from medicine
Medical people/data cannot block doctorate
Plan A/B dependencies and fallback
Slide
3
4
2,4
5,10
1,10
2,12
3,6
2,8,9
6,9,10
6
Current state
Awaiting
Awaiting
Awaiting
Partial
Blocked
Partial
Awaiting
Awaiting
Partial
Partial
Notes: Use only if a requirement-specific question arises.
[Sources]
- docs/research/phd-proposal/iris-requirements-closure-audit.md

## Slide 14
Appendix · Requirements R-11–R-19
A2
Medical, cadence, literature, workspace, schedule and Penina controls.
ID
R-11
R-12
R-13
R-14
R-15
R-16
R-17
R-18
R-19
Control
Bounded medical familiarization
VDI/privacy/local-offline controls
Short weekly task-focused cadence
Next package: RQs, literature, workbook
One paper per row; synthesis separated
Living taxonomy and gap resource
Working/source Drive separation
September draft / October target
Penina work reused with provenance
Slide
9
9
10,12
3,4,7,10
7
7
10
10
10,A7
Current state
Partial
Blocked
Partial
Partial
Partial
Partial
Partial
Partial
Partial
Notes: Use only if a requirement-specific question arises.
[Sources]
- docs/research/phd-proposal/iris-requirements-closure-audit.md

## Slide 15
Appendix · Actions A-01–A-08
A3
Two actions are narrowly verified; all other actions retain their current gate.
ID
A-01
A-02
A-03
A-04
A-05
A-06
A-07
A-08
Action
Draft RQs and study map
Begin literature review
Build and seed literature matrix
Create working area and confirm access
Share source resources viewer-only
Finalize Wednesday invitation
Run one-task weekly cycle
Bounded medical-resource inspection
Slide
3,4
7
7
10
9,10
10
12
9
Current state
Partial
Partial
Verified
Partial
Partial
Verified
Partial
Partial
Notes: Do not equate an artifact draft with delivered or accepted work.
[Sources]
- docs/research/phd-proposal/iris-requirements-closure-audit.md

## Slide 16
Appendix · Actions A-09–A-15
A4
Blocked and partial actions retain their human, institutional, or evidence gates.
ID
A-09
A-10
A-11
A-12
A-13
A-14
A-15
Action
Validate medical route and approvals
Draft Plan A/B and trigger
Document VDI and model constraints
Produce developed proposal draft
Prepare full submission
Verify university process
Clarify partner meeting/status
Slide
9
6
9
10
10
10
9,10
Current state
Blocked
Partial
Partial
Partial
Open
Open
Blocked
Notes: Do not equate an artifact draft with delivered or accepted work.
[Sources]
- docs/research/phd-proposal/iris-requirements-closure-audit.md

## Slide 17
Appendix · Questions Q-01–Q-10
A5
Questions close only through an explicit accountable decision or authoritative evidence.
ID
Q-01
Q-02
Q-03
Q-04
Q-05
Q-06
Q-07
Q-08
Q-09
Q-10
Question
Final U-RQ and SQ wording
Whether/how medicine is used
Plan A/B boundary and trigger
Literature taxonomy and fields
MIMIC selection and governance
Approved local/offline models
Calendar and Drive permissions
Official candidacy policy
Clalit use case and prerequisites
Partner meeting/mechanism/second partner
Slide
3,11
6,9
6,11
7
9
9
10
10
9
9
Current state
Open
Blocked
Awaiting
Open
Blocked
Blocked
Partial
Open
Blocked
Blocked
Notes: Silence remains Deferred.
[Sources]
- docs/research/phd-proposal/iris-requirements-closure-audit.md

## Slide 18
Claim states
A6
A stronger wording requires stronger evidence; planned work never becomes a result by repetition.
State
Established
Preliminary
Planned
Blocked
Partner-dependent
Use when
Narrow artifact/integrity fact is locally verified
Evidence exists but validation is incomplete
Protocol or deliverable has not run
A required prerequisite is absent
External people/access/approval control progress
Example in this package
44 controls captured; calendar accepted
Novelty and doctoral adequacy
Scientific experiments and proposal milestones
EXP-005 labels; medical gates
Clalit route and clinical feasibility
Notes: Keep claim state visible before discussing results.
[Sources]
- docs/research/phd-proposal/claim-register.md

## Slide 19
Bilingual alignment is complete; human review has not run
A7
Machine alignment provides full chronology. It does not establish translation accuracy, speaker identity, or quotation readiness.
1,195
aligned segments
Hebrew ASR + machine English + transcript anchors
910
currently control-linked
285 segments need explicit human disposition
0
dual-reviewed rows
Reviewer A, Reviewer B and adjudication remain pending
Notes: Appendix — Do not show or read a direct quote. The ledger is a review interface, not a completed review.
Only S-0001–S-0006 have pre-existing high-confidence named Iris attribution.
[Sources]
- docs/research/meetings/2026-07-29-iris-supervisor-provenance-manifest.md
- outputs/iris-closure-2026-08-01/Iris_Zoom_Review_Ledger_2026-07-29.xlsx

## Slide 20
Appendix · Scientific experiments align to the three studies
A8
These are protocols and crosswalks—not completed outcomes.
Plan label
SCI-EXP-01
SCI-EXP-02
SCI-EXP-03
SCI-EXP-04
SCI-EXP-05
SCI-EXP-06
Canonical experiment route
EXP-006–008, 013–016
EXP-017–018, 022
EXP-022, 026
EXP-025
Conditional medical protocol
EXP-026–027
Study
Selective intervention
Governed reuse
Longitudinal reuse
Plan B transfer
Plan A transfer
Effort/ablation
Gate
Mechanism evidence only
No beneficial-reuse claim
Human protocol required
Authorized second context
G1–G6 all pass
Independent labels + usability
Notes: Use this crosswalk to avoid creating duplicate canonical experiment IDs.
[Sources]
- docs/research/phd-proposal/scientific-experiment-crosswalk.md
- experiments/registry.md

## Slide 21
Appendix · Package status and release gates
A9
Built artifacts are not automatically reviewed, rehearsed, delivered, or accepted.
Artifact/gate
PPTX + PDF + notes
Zoom review ledger
Live rehearsal
Drive delivery/access
Supervisor acceptance
Final closure
Current state
Built locally; automated QA passed
1,195 machine-preliminary rows
NOT RUN
NOT SHARED / NOT TESTED
0/19
BLOCKED
Release condition
PowerPoint visual, link and claim checks passed
Two reviewers + adjudication
Dated human record and corrections
Ali review + two recipient tests
Explicit dispositions and read-back
Extraction + implementation + signed acceptance
Notes: End appendix with the exact release boundary.
[Sources]
- docs/research/meetings/2026-08-05-supervisor-presentation-manifest.md
- docs/research/meetings/2026-08-05-supervisor-rehearsal-record.md
- docs/research/meetings/2026-08-05-supervisor-delivery-access-record.md